## Agile Backlog 1
Iteration 1 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 101. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD Est. | By | Priority
101 | Develop Login Page functionality | 5 | UI Developer | High
102 | Implement Dashboard for user overview | 8 | Frontend Developer | High
103 | Setup Backend Authentication API | 6 | Backend Developer | Medium
104 | Design Initial UI Mockups | 4 | UX Designer | Medium
…
Iteration 2
201 | Develop Debugging Assistance Page | 7 | AI Developer | High
202 | Implement Sprint Planning Tool | 6 | Frontend & Backend Team | Medium
203 | Integrate Real-time Collaboration Module | 9 | AI & Backend Engineers | High
Iteration 3
301 | Create Learning Resources Page | 8 | AI Team, Frontend Developer | High
302 | Complete Live Collaboration Page | 10 | Frontend & QA Engineers | High
303 | System Testing and Final Deployment | 12 | QA Team, All Developers | High
Low Priority (pink)

## Iteration 1 Plan
Iteration Plan 1
Project | AI CodeCraft: Revolutionizing Software Development with Intelligent Assistance
Team Names: | RAYAPATI HARI CHANDRA PRASAD (9015953), YUAN HAIBO (9010929), RUTVIK KUMAR NARSHIBHAI BHADANI (9032172), PUJABEN SUBASCHANDRA PATEL (9031577)
Team Number: | 1
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan Adherence?
101 | Develop Login Page functionality | UI Dev | On Track
102 | Implement Dashboard for user overview | FE Dev | On Track
103 | Setup Backend Authentication API | BE Dev | On Track
104 | Design Initial UI Mockups | UX | On Track
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Frontend: React.js | Complexity in handling dynamic UI interactions | UX Designer (UX)
Backend: Node.js | Scalability for high user concurrency | Backend Engineer (BE)
Database: MongoDB | Optimizing queries for large datasets | Database Administrator (DBA)
Development Environment: Visual Studio Code | Ensuring consistent extensions and environment setup | All Developers (RD, YH, PB)
AI Integration: OpenAI APIs | Latency in real-time debugging suggestions | AI Engineer (AI)
3. Did your team visually track your progress by using tools such as Microsoft Project, SharePoint, Trello, etc.? Explain why you choose this tool.
Tracking Software Used | Why?
Trello | Easy to visually manage tasks with Kanban boards, assign responsibilities, and track progress.
Microsoft Project | Useful for detailed task scheduling and tracking resource allocation.
GitHub | Facilitates version control and collaboration on code across team members.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 1
Iteration 1: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception PD | Iteration #1 PD | Iteration #2 PD | Iteration #3 PD | Transition PD
|  | Due: | Due: | Due: | Due: | Due:
101 | Login Page | 0 | 5 | 0 | 0 | 0
102 | User Dashboard | 0 | 8 | 0 | 0 | 0
103 | Authentication API | 0 | 6 | 0 | 0 | 0
104 | UI Mockups | 0 | 4 | 0 | 0 | 0
201 | Debugging Assistance Page | 0 | 0 | 7 | 0 | 0
202 | Sprint Planning Tool | 0 | 0 | 6 | 0 | 0
203 | Collaboration Module | 0 | 0 | 9 | 0 | 0
301 | Learning Resources Page | 0 | 0 | 0 | 8 | 0
302 | Live Collaboration | 0 | 0 | 0 | 10 | 0
303 | Testing and Deployment | 0 | 0 | 0 | 12 | 2
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 92 | 88 | 120 | 8
Total Project Hours |  | 308

## Agile Backlog 2
Iteration 2 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD Est. | By | Priority
High Priority
Iteration 1
201 | Develop Debugging Assistance Page | 7 | AI Developer | High
202 | Implement Sprint Planning Tool | 6 | Frontend & Backend Team | Medium
203 | Integrate Real-time Collaboration Module | 9 | AI & Backend Engineers | High
Iteration 2
Iteration 3
Medium Priority
Number | Description | PD est. | By
None | None | None | None
Low Priority
Number | Description | PD est. | By
None | None | None | None

## Iteration 2 Plan
Iteration Plan 2
Project | AI CodeCraft: Revolutionizing Software Development with Intelligent Assistance
Team Names: | RAYAPATI HARI CHANDRA PRASAD (9015953), YUAN HAIBO (9010929), RUTVIK KUMAR NARSHIBHAI BHADANI (9032172), PUJABEN SUBASCHANDRA PATEL (9031577)
Team Number: | 1
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
201 | Develop Debugging Assistance Page | AI Dev | On Track
202 | Implement Sprint Planning Tool | FE & BE | On Track
203 | Integrate Real-time Collaboration Module | AI & BE | On Track
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Testing Tools: Jest and Selenium | Ensuring full coverage and usability issues | QA Engineer (QA)
Collaboration Framework: Socket.IO | Real-time synchronization for collaboration features | Backend Engineer (BE)
AI APIs: OpenAI APIs | Latency in debugging assistance suggestions | AI Engineer (AI)
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
Trello | Used to track tasks visually with Kanban boards. Iteration 2 progress tracked for jobs and dashboard.
GitHub | Tracks code versioning for backend and frontend development.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 2
Iteration 2: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and tasks must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
201 | Develop Debugging Assistance Page | 0 | 0 | 7 | 0 | 0
202 | Implement Sprint Planning Tool | 0 | 0 | 6 | 0 | 0
203 | Integrate Real-time Collaboration Module | 0 | 0 | 9 | 0 | 0
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 0 | 88 | 0 | 0
Total Project Hours |  | 88

## Agile Backlog 3
Iteration 3 Backlog
Notes Iteration 1, all numbers begin with 101 and continue upward. In Iteration 2, all numbers start with 201 and continue upward. In Iteration 3, all numbers begin with 301 and continue upward. Start number column from 201. Outside requirements such as Inception pieces or other requirements are numbered 1-100. PD = Person Day and the number of hours they will spend on a task. Only high-priority items are prioritized, assigned to iteration, and estimated.
Number | Description | PD Est. | By | Priority
High Priority
Iteration 1
301 | Create Learning Resources Page | 8 | AI Team, Frontend Developer | High
302 | Complete Live Collaboration Page | 10 | Frontend & QA Engineers | High
303 | System Testing and Final Deployment | 12 | QA Team, All Developers | High
Iteration 2
Iteration 3
Medium Priority
At this stage, Iteration 3 focuses on high-priority tasks to finalize the product. No medium-priority tasks are assigned.
Low Priority

## Iteration 3 Plan
Iteration Plan 3
Project | AI CodeCraft: Revolutionizing Software Development with Intelligent Assistance
Team Names: | RAYAPATI HARI CHANDRA PRASAD (9015953), YUAN HAIBO (9010929), RUTVIK KUMAR NARSHIBHAI BHADANI (9032172), PUJABEN SUBASCHANDRA PATEL (9031577)
Team Number: | 1
1. What deliverables did the team plan to complete by the end of the iteration? Refer to your Project Plan submitted in Week 3 to determine which items should be completed. Please note that dates may change as the Iterations continue and various issues arise. Did this Iteration include other work items such as setting up a development environment or bug fixes in the Iteration backlog list?
Number | Description | Responsibility (Initials) | Project Plan adherence?
301 | Create Learning Resources Page | AI, FE Dev | On Track
302 | Complete Live Collaboration Page | FE & QA | On Track
303 | System Testing and Final Deployment | QA Team, Devs | On Track
2. Did the team identify the architecture (hardware/software/platform/solution design) early? Was there a architecture owner assigned?
List of architecture being used | Concerns (current and potential) | Owner Assigned (Initials)
Frontend: React.js | Complexity in integrating new features | UX Designer (UX)
Backend: Node.js | Performance bottlenecks in scheduling logic | Developer (PB)
Database: MongoDB | Query optimization for scheduling meetings | Database Admin (DBA)
Testing Tools: Jest and Selenium | Testing edge cases for scheduling and Ask Me | QA Engineer (QA)
3. Is your team still using the tracking software for your project? Are there any significant timeline changes to your project?
Tracking Software | Progress & Updates
Trello | Used to track tasks for meeting scheduling, Ask Me, and deployment. Updates synced with team.
GitHub | Ensures version control for the final deployment and documentation process.
The point of the Iteration Plan is to have a goal set from the backlog. Iteration Plan and backlog are submitted prior to each iteration. Iteration Plans can repeat work items if feedback is provided by the client that further updates are required for a deliverable. Each iteration should have a working code demostration.
Note: These guiding questions are not meant to be exhaustive. Each team is responsible for the delivery of a workable solution.

## Agile Release Summary 3
Iteration 3: Release Plan Summary
Note The top row lists Number, Feature/Requirement, Inception, Iterations 1, 2, and 3, and Transition. The Number and Feature/Requirements column information is provided in your backlog. The numbers and task must match the backlog information. Once this information is inputted into your release summary chart your team will determine what iteration the tasks will be completed and how many hours are needed to complete each task. Each group should expect to work 9 person-days (PD) per week. A reminder that 1 person day is equal to 4 person hours.
Colour Coding
Inception and Other Requirements (gray) | Iteration 1 (orange) | Iteration 2 (light Blue) | Iteration 3 (light yellow) | Transition (light green)
Number | Feature / Requirement | Inception | Iteration #1 | Iteration #2 | Iteration #3 | Transition
|  | Due: | Due: | Due: | Due: | Due:
301 | Learning Resources Page | 0 | 0 | 0 | 8 | 0
302 | Live Collaboration | 0 | 0 | 0 | 10 | 0
303 | Testing and Deployment | 0 | 0 | 0 | 12 | 2
Work Effort in Person Days (PD) 1 PD hour equals 4 hours |  | 0 | 0 | 0 | 120 | 8
Total Project Hours |  | 128